## Sheet1
Task | Status | Stage | Due date | Notes
Conceptualization/Idea Brainstorming | Completed | Content | Jul 31st, 2025
Moodboard creation | Completed | Visual Design | Jul 31st, 2025
Set Mechanic | Completed | Content | Jul 31st, 2025
Set Mechanic UI concept | Completed | Visual Design | Jul 31st, 2025
Unit Roster/Skins | Completed | Visual Design | Aug 31st, 2025
Origins | Completed | Content | Aug 31st, 2025
Classes | Completed | Content | Aug 31st, 2025
Trait Webbing/Unit distribution | Completed | Content | Aug 31st, 2025
Unit Abilities | Completed | Content | Sep 30th, 2025
Unit Stats | Completed | Content | Sep 30th, 2025
Iconography | Completed | Visual Design | Oct 31st, 2025
Visual Unit assets | Completed | Visual Design | Oct 31st, 2025
Visual Origin/Class assets | Completed | Visual Design | Oct 31st, 2025
Website Creation/Design | In progress | Visual Design | Nov 30th, 2025
Documentation organization/update | Not started | Documentation | Nov 30th, 2025
Augments | In progress | Content | Dec 31st, 2025
Visual Augment assets | Not started | Visual Design | Dec 31st, 2025
Example Boards/Theorycrafting | Not started | Content | Dec 31st, 2025
Rationale of Process/Write up | In progress | Documentation | Dec 31st, 2025
Unreal Blueprint Combat Simulation | Not started | Balance | Jan 31st, 2025
Simulation Write up | Not started | Documentation | Jan 31st, 2025
Data Revision/CleanUp | Not started | Documentation | Jan 31st, 2025
Project 100% Completed | In progress |  | Jan 31st, 2025